## Sprint 1
Sprint 1
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Draw ERD | Draw ERD diagram | ThinhLP | Done | 14 | 3 | 2 | 1 | 1 | 1 | 2
Draw usecase diagram | Draw usecase diagram | ThinhLP | Done | 12 | 0.5 | 2 | 3.5 | 2 | 2.5 | 3
Design manage page mockup | Manage User page | AnhDT | Done | 10 | 2 | 3 | 2 | 2 | 1.5 | 0.5
| Manage Plan page | ThinhLP | Done | 10 | 1.5 | 2 | 1.5 | 3 | 4 | 1
| Manage Course page | NguyenVT | Done | 10 | 2.5 | 2 | 2 | 2 | 0.5 | 1
| Manage Brand page | AnhDT | Done | 10 | 3 | 2 | 0.5 | 2 | 1.5 | 1
| Manage skill page | NguyenVT | Done | 10 | 3 | 1 | 2 | 2 | 1 | 0.5
Design learner page mockup | Learner plan page | NguyenVT | Done | 10 | 2 | 2 | 2 | 2.5 | 0.5 | 1
| Plan overview page | AnhDT | Done | 8 | 0 | 2 | 3 | 1 | 1 | 1
| User profile page | HungPC | Done | 8 | 2 | 1 | 2 | 1.5 | 2 | 0.5
| Learning page - Video lecture, text lecture, slideshow | HungPC | Done | 8 | 2 | 3 | 1 | 0.5 | 0.5 | 1
| Learning page - Quiz lecture | HungPC | Done | 8 | 3 | 1.5 | 1.5 | 0.5 | 0.5 | 1
| Login page | AnhDT | Done | 8 | 2.5 | 0 | 2 | 0 | 3 | 0.5
Report 1 | Introduction, current situation | NguyenVT | Done | 4 | 0 | 0 | 1.5 | 1 | 2.5 | 1
| Problem definition | HungPC | Done | 4 | 1 | 1 | 0 |  | 1 | 1
| Proposed solution | NguyenVT | Done | 4 | 0 | 0.5 | 0 | 1 | 1.5 | 1
| Functional requirement, role responsibility | HungPC | Done | 4 | 1 | 1 | 0.5 | 0.5 | 0.5 | 1
| Total |  |  | 142 | 29 | 26 | 26 | 22.5 | 25 | 18

## Sprint 2
Sprint 2
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Fix diagram | Fix ERD | ThinhLP | Done | 6 | 0 | 1 | 2 | 2.5 | 2 | 1
Implement manage page prototype | Master page | ThinhLP | Done | 8 | 2 | 2 | 1 | 1 | 1.5 | 0.5
| Manage user page | AnhDT | Done | 14 | 3 | 4 | 1.5 | 0.5 | 2.5 | 0.5
| Manage brand page | HungPC | Done | 14 | 3 | 1 | 2 | 3 | 2.5 | 0.5
| Manage course page | NguyenVT | Done | 16 | 4 | 3 | 3 | 1.5 | 3 | 0.5
| Manage skill page | AnhDT | Done | 14 | 3 | 2 | 4 | 1 | 3.5 | 0.5
Implement learner page prototype | Learner page | HungPC | Done | 14 | 2 | 2.5 | 3.5 | 2 | 2.5 | 0.5
| User plan page | NguyenVT | Done | 14 | 2 | 2 | 4 | 2.5 | 0.5 | 0.5
| Plan overview page | ThinhLP | Done | 16 | 4 | 3 | 3 | 2.5 | 2 | 0.5
| Login page | AnhDT | Done | 10 | 2 | 2 | 2 | 1.5 | 2 | 0.5
Report 2 | Problem definition | HungPC | Done | 6 | 1.5 | 0.5 | 1.5 | 1.5 | 1.5 | 0.5
| Project Organization | HungPC | Done | 6 | 1.5 | 2.5 | 1 | 0.5 | 0.5 | 0.5
| Project Management | NguyenVT | Done | 6 | 1 | 0.5 | 0.5 | 3 | 0.5 | 0.5
| Coding convention | NguyenVT | Done | 6 | 1 | 1 | 0 | 0 | 2.5 | 0.5
| Total |  |  | 150 | 30 | 27 | 29 | 23 | 27 | 7.5

## Sprint 3
Sprint 3
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Draw class diagram | Draw class diagram | ThinhLP | Done | 15 | 3 | 3 | 2 | 1 | 4 | 3
Draw sequence diagram | - Learner: Learn lecture | HungPC | In process | 6 | 1 | 1 | 1 | 0.5 | 1.5
| - Learner: Take quiz | HungPC | Todo | 6 | 0 | 0 | 0 | 0 | 0
| - Author: Create course | AnhDT | In process | 6 | 0 | 0.5 | 0 | 0.5 | 0
| - Author: Update course | ThinhLP | Todo | 6
| - Author: Remove course | HungPC | In process | 6 | 1 | 2 | 2 | 2 | 2
| - Manager: Create plan | NguyenVT | Done | 6 | 2 | 2 | 1 | 0.5 | 0 | 0.5
| - Manager: Update plan | NguyenVT | Done | 6 | 0.5 | 2 | 1 | 1 | 1 | 0.5
| - Manager: Remove plan | HungPC | Done | 6 | 1 | 1 | 0.5 | 3.5 | 0.5 | 0.5
| - Manager: Add learner to plan | NguyenVT | Done | 6 | 0.5 | 2 | 1 | 0 | 3 | 0.5
| - Manager: Create program | AnhDT | Done | 6 | 2.5 | 1.5 | 0 | 0.5 | 1 | 0.5
| - Manager: Update program | NguyenVT | Done | 6 | 0 | 0 | 2 | 2.5 | 1 | 0.5
| - Manager: Remove program | HungPC | Done | 6 | 1.5 | 1 | 0.5 | 0 | 2.5 | 0.5
| - Unauthorized user: Log in | AnhDT | Done | 4 | 2 | 0 | 2 | 0 | 0.5 | 0.5
Draw physical diagram | Draw physical diagram | ThinhLP | Done | 10 | 4 | 4 | 2.5 | 0.5 | 2 | 2
Demo Playframework | Demo CRUD project with Playframework | NguyenVT | Done | 15 | 5 | 2 | 3 | 3 | 1 | 1
| Demo CRUD project with Playframework | HungPC | Done | 15 | 4 | 2 | 3 | 1 | 1 | 1
| Demo CRUD project with Playframework | AnhDT | Done | 15 | 3 | 3 | 4 | 3 | 3.5 | 1
| Total |  |  | 146 | 31 | 27 | 25.5 | 19.5 | 24.5 | 12

## Sprint 4
Sprint 4
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Complete sequence diagram | - Learner: Learn lecture | HungPC | Done | 3 | 3 | 0 | 0 | 0 | 0 | 0.5
| - Learner: Take quiz | HungPC | Done | 3 | 0 | 3 | 0 | 0 | 0 | 0.5
| - Author: Create course | HungPC | Done | 3 | 0 | 0 | 3 | 0 | 0 | 0.5
| - Author: Update course | HungPC | Done | 3 | 0 | 0 | 0 | 3 | 0 | 0.5
| - Author: Remove course | HungPC | Done | 3 | 0 | 0 | 0 | 0 | 3 | 0.5
| - Unauthorized user: Log in | NguyenVT | Done | 3 | 0 | 0.5 | 1 | 0 | 1 | 0.5
Implement manage page prototype | - Manage course page | NguyenVT | Done | 8 | 2 | 1.5 | 2 | 1.5 | 2.5 | 0.5
| - Manage plans list | NguyenVT | Todo | 5
| - Manage plan | ThinhLP | In process | 10 | 3 | 2 | 2 | 1 | 1.5
| - Manage user page | AnhDT | Done | 4 | 1 | 0 | 1.5 | 1 | 0 | 0.5
Implement learner page prototype | - Learning page (Quiz) | HungPC | Done | 8 | 3 | 1.5 | 1 | 1 | 1 | 0.5
| - Learning page (Text / powerpoint / video) | AnhDT | Done | 8 | 2 | 2 | 2 | 1.5 | 0 | 0.5
| - View quiz result page | AnhDT | Done | 10 | 3 | 2 | 2 | 2 | 1 | 0.5
| - User plan page | ThinhLP | Done | 4 | 2 | 1 | 1.5 | 0 | 0 | 0.5
| - Plan overview page | NguyenVT | Done | 4 | 0 | 1 | 0.5 | 2 | 1 | 0.5
Create structure for backend + security | Create structure for backend + security | ThinhLP | Done | 6 | 2 | 3 | 1 | 0 | 0.5 | 0.5
Implement manage course APIs | - Get course (all, by plan, by program, by user) | HungPC | Done | 3 | 2 | 1 | 0 | 0 | 1 | 0.5
| - Create course | ThinhLP | Done | 4 | 0.5 | 0 | 0 | 2 | 1 | 0.5
| - Update course basic information | HungPC | Todo | 3 | 0 | 2 | 2 | 0 | 0
| - Remove course | HungPC | Todo | 3 | 0 | 0 | 1 | 2 | 1
Implement manage program APIs | - Create program | AnhDT | Done | 3 | 1 | 0.5 | 0 | 1 | 1 | 0.5
| - Update program | AnhDT | Done | 3 | 1 | 1 | 1 | 0.5 | 0 | 0.5
| - Remove program | AnhDT | Todo | 3
| - Get all program | AnhDT | Done | 3 | 0 | 0 | 1 | 1 | 2 | 0.5
Implement manage plan APIs | - Get plan (all, by user) | HungPC | Done | 3 | 0 | 0 | 0 | 1.5 | 1.5 | 0.5
| - Create plan | NguyenVT | Done | 3 | 1 | 1.5 | 0.5 | 0.5 | 0 | 0.5
| - Update plan | NguyenVT | Done | 4 | 1 | 1 | 1 | 0.5 | 0 | 0.5
| - Remove plan | NguyenVT | Done | 3 | 1 | 1 | 0.5 | 2 | 0 | 0.5
Implement manage user APIs | - Create user | AnhDT | Todo | 3
| - Update user basic information | AnhDT | Todo | 3
| - Update user account | ThinhLP | Done | 3 | 0.5 | 0 | 0 | 1 | 2 | 0.5
Implement manage discussion APIs | - Add discussion | ThinhLP | Done | 3 | 0 | 1 | 1 | 1 | 1 | 0.5
| - Remove discussion | NguyenVT | Done | 4 | 1 | 0.5 | 1.5 | 0 | 1 | 0.5
| - Edit discussion content | NguyenVT | Done | 4 | 2 | 0.5 | 0.5 | 0.5 | 1 | 0.5
Login page | Login Page | ThinhLP | Done | 3 | 0 | 1 | 1.5 | 1 | 0.5 | 0.5
| Total |  |  | 146 | 32 | 28.5 | 29 | 27.5 | 24.5 | 14

## Sprint 5
Sprint 5
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Implement prototype (HTML, CSS, JS) | - Manage plans list | NguyenVT | Done | 3 | 3 | 0 | 0 | 0 | 0 | 0.5
| - Finish manage plan | ThinhLP | Done | 5 | 5 | 0 | 0 | 0 | 0 | 0.5
Complete manage course APIs | - Update course basic information | ThinhLP | Done | 3 | 3 | 0 | 0 | 0 | 0 | 0.5
| - Remove course | ThinhLP | Done | 3 | 0 | 3 | 0 | 0 | 0 | 0.5
Complete manage program APIs | - Remove program | HungPC | Done | 3 | 3 | 0 | 0 | 0 | 0 | 0.5
Complete manage plan APIs | - Remove plan | NguyenVT | Done | 3 | 3 | 0 | 0 | 0 | 0 | 0.5
| - Add user to plan | ThinhLP | Todo | 3
Implement manage user APIs | - Create user | AnhDT | Done | 3 | 3 | 0 | 0 | 0 | 0 | 0.5
| - Update user basic information | AnhDT | Done | 3 | 3 | 0 | 0 | 0 | 0 | 0.5
Implement manage section APIs | - Create section | HungPC | Done | 3 | 3 | 0 | 0 | 0 | 0 | 0.5
| - Update section | HungPC | Done | 3 | 2 | 1 | 0 | 0 | 0 | 0.5
| - Reorder section | HungPC | Todo | 3
| - Remove section | HungPC | Todo | 3
Implement manage lecture APIs | - Create simple lecture (title, type) | NguyenVT | Done | 3 | 2 | 1 | 0 | 0 | 0 | 0.5
| - Update lecture (title, status, note) | NguyenVT | Done | 3 | 0 | 3 | 0 | 0 | 0 | 0.5
| - Remove lecture | NguyenVT | Done | 3 | 0 | 3 | 0 | 0 | 0 | 0.5
Implement manage brand APIs | - Create brand | AnhDT | Done | 3 | 2 | 1 | 0 | 0 | 0 | 0.5
| - Update brand | AnhDT | Done | 3 | 0 | 3 | 0 | 0 | 0 | 0.5
| - Remove brand | AnhDT | Done | 3 | 0 | 3 | 0 | 0 | 0 | 0.5
Implement manage skill APIs | - Create skill | AnhDT | Done | 3 | 0 | 1 | 2 | 0 | 0 | 0.5
| - Update skill | AnhDT | Done | 3 | 0 | 0 | 3 | 0 | 0 | 0.5
| - Remove skill | AnhDT | Done | 3 | 0 | 0 | 3 | 0 | 0 | 0.5
Implement manage pages | - Manage plan list | ThinhLP | Done | 4 | 0 | 3 | 1 | 0 | 0 | 0.5
| - Manage plan page (include program) | ThinhLP | In process | 14 | 0 | 2 | 6 | 5 | 5
| - Manage course page | NguyenVT | In process | 14 | 0 | 1 | 8 | 2 | 2
| - Manage user | HungPC | Done | 10 | 0 | 7 | 3 | 0 | 0 | 0.5
| - Manage brand | HungPC | In process | 10 | 0 | 0 | 5 | 5 | 2
| - Manage skill | AnhDT | In process | 10 | 0 | 0 | 0 | 8 | 8
| Total |  |  | 130 | 32 | 32 | 31 | 20 | 17 | 10.5

## Sprint 6
Sprint 6
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Finish manage plan APIs | - Add user to plan | ThinhLP | Done | 3 | 0 | 0 | 3 | 0 | 0 | 0.5
Finish manage section APIs | - Reorder section | HungPC | Done | 4 | 4 | 0 | 0 | 0 | 0 | 0.5
| - Remove section | HungPC | Done | 3 | 2 | 1 | 0 | 0 | 0 | 0.5
Finish manage lecture APIs | - Reorder lecture | HungPC | Done | 5 | 2 | 3 | 0 | 0 | 0 | 0.5
Implement manage quiz APIs | - Update quiz information | NguyenVT | Done | 5 | 5 | 0 | 0 | 0 | 0 | 0.5
| - Create question | NguyenVT | Done | 5 | 0 | 5 | 0 | 0 | 0 | 0.5
| - Update question (content, type) | NguyenVT | Done | 5 | 0 | 0 | 5 | 0 | 0 | 0.5
| - Remove question | NguyenVT | Done | 4 | 0 | 0 | 0 | 5 | 0 | 0.5
| - Reorder question | HungPC | Done | 4 | 0 | 4 | 0 | 0 | 0 | 0.5
| - Create answer | HungPC | Done | 5 | 0 | 0 | 5 | 0 | 0 | 0.5
| - Update answer | HungPC | Done | 5 | 0 | 0 | 0 | 3 | 2 | 0.5
| - Remove answer | HungPC | Done | 5 | 0 | 0 | 0 | 3 | 2 | 0.5
Implement manage pages | - Finish manage plan page (include program) | ThinhLP | Done | 25 | 8 | 8 | 5 | 4 | 0 | 1
| - Finish manage course page | NguyenVT | In process | 30 | 3 | 3 | 3 | 3 | 8
| - Manage brand | HungPC | Done | 10 | 0 | 0 | 3 | 3 | 3 | 1
| - Manage brand detail | HungPC | Done | 10 | 1 | 1 | 2 | 1 | 3 | 1
| - Manage skill | AnhDT | Done | 10 | 5 | 2 | 2 | 1 | 0 | 1
| - Manage user | AnhDT | Done | 10 | 3 | 4 | 4 | 0 | 0 | 1
| Total |  |  | 148 | 33 | 31 | 32 | 23 | 18 | 11

## Sprint 7
Sprint 7
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Implement upload APIs | - Upload video | NguyenVT | Done | 10 | 4 | 3 | 3 | 0 | 0 | 0.5
| - Upload text lecture | ThinhLP | Done | 10 | 5 | 3 | 2 | 0 | 0 | 0.5
| - Upload powerpoint lecture | HungPC | Done | 10 | 4 | 6 | 0 | 0 | 0 | 0.5
Implement manage page | - Finish manage course page | NguyenVT | In process | 14 | 4 | 3 | 3 | 4 | 0 | 1
| - Manage lecture page (video lecture) | NguyenVT | Done | 15 | 0 | 2 | 2 | 4 | 8 | 1
| - Implement statistic page | Hung PC | Todo | 10 | 4 | 4 | 2 | 0 | 0 | 1
Implement learner page | - Plan overview page (author, learner) | HungPC | Done | 10 | 0 | 0 | 3 | 3 | 4 | 1
| - Learning page (video/text) | ThinhLP | In process | 15 | 3 | 3 | 3 | 4 | 0
| - User plans page | AnhDT | Done | 15 | 5 | 4 | 2 | 2 | 2 | 1
| - User profile | AnhDT | In process | 15 | 3 | 4 | 2 | 6 | 6
Research | - Wowza streaming server + wowza player | ThinhLP | Done | 10 | 0 | 2 | 3 | 0 | 5 | 1
| - Powerpoint plugin | HungPC | Done | 10 | 0 | 0 | 3 | 5 | 4 | 1
| Total |  |  | 144 | 32 | 34 | 28 | 28 | 29 | 8.5

## Sprint 8
Sprint 8
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Implement manage report prototype | Report page | NguyenVT | In process | 15 | 4 | 3 | 4 | 2 | 2
Implement statistic API | - Statistic API (student monthly, ...) | ThinhLP | Done | 15 | 5 | 5 | 5 | 0 | 0 | 1
Implement manage pages | - Complete manage course page | NguyenVT | Done | 3 | 3 | 0 | 0 | 0 | 0 | 1
| - Implement statistic page | Hung PC | Todo | 15 | 5 | 4 | 3 | 2 | 1
Implement learner pages | - Course overview page | AnhDT | In process | 20 | 4 | 7 | 4 | 3 | 2
| - Learning page (video/text) | ThinhLP | Done | 10 | 3 | 3 | 3 | 7 | 7 | 1
| - Learning page (powerpoint) | HungPC | Done | 20 | 2 | 4 | 3 | 3 | 6 | 1
| - Take quiz page | NguyenVT | Done | 20 | 0 | 5 | 5 | 5 | 5 | 1
| - Quiz result page | HungPC | In process | 10 | 1 | 1 | 3 | 3 | 2
| - Complete user profile | AnhDT | Done | 5 | 4 | 1 | 4 | 5 | 6 | 1
| Total |  |  | 133 | 31 | 33 | 34 | 30 | 31 | 6

## Sprint 9
Sprint 9
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Implement report page | - Implement report page | Hung PC | In process | 15 | 4 | 4 | 2 | 0 | 0
| - Implement report detail page | ThinhLP | In process | 20 | 4 | 4 | 6 | 6 | 2
Implement learner page | - Course overview page | AnhDT | Done | 5 | 3 | 2 | 0 | 0 | 0 | 1
| - Quiz result page | HungPC | Done | 8 | 4 | 2 | 2 | 0 | 0 | 1
| - Improve search & pagination | NguyenVT | Done | 20 | 5 | 5 | 4 | 4 | 2 | 1
| - Discussion in learning page | NguyenVT | Done | 10 | 3 | 3 | 2 | 2 | 0 | 1
Fix bug | - Update answer bug | HungPC | Done | 10 | 0 | 2 | 2 | 3 | 3 | 1
| - Validate program startdate | NguyenVT | Done | 5 | 0 | 0 | 2 | 2 | 1 | 1
| - Hide no-course-program in plan overview page | AnhDT | Done | 10 | 3 | 4 | 2 | 1 | 1 | 1
Document (Report 3) | User specification
| - Admin use cases | AnhDT | Done | 13 | 2 | 2 | 6 | 3 | 0 | 1
| - Manager use cases | NguyenVT | Done | 13 | 0 | 0 | 0 | 1 | 5 | 1
| - Learner use cases | ThinhLP | Done | 13 | 4 | 4 | 2 | 2 | 2 | 1
| - Author use cases | HungPC | Done | 13 | 0 | 0 | 1 | 5 | 5 | 1
| Total |  |  | 155 | 32 | 32 | 31 | 29 | 21 | 11

## Sprint 10
Sprint 10
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Implement manage report page | - Implement report page | Hung PC | Done | 5 | 4 | 1 | 0 | 1 | 1 | 1
| - Implement report detail page (instructor) | ThinhLP | Done | 5 | 2 | 2 | 1 | 2 | 0 | 1
Fix bugs | - Remove plan bug | HungPC | Done | 5 | 2 | 2 | 3 | 0 | 0 | 1
| - Reorder question bug | NguyenVT | Done | 5 | 4 | 2 | 0 | 0 | 0 | 1
| - Check authority for APIs | NguyenVT | Done | 7 | 2 | 3 | 1 | 0 | 0 | 1
Document | Report 3
| Conceptual diagram | HungPC | Done | 15 | 2 | 5 | 4 | 5 | 5 | 1
Report 4
| Design overview | AnhDT | Done | 10 | 3 | 3 | 2 | 1 | 1 | 1
| System architectual design | NguyenVT | Done | 10 | 2 | 2 | 5 | 1 | 0 | 1
| Component diagram | ThinhLP | In process | 15 | 4 | 4 | 3 | 3 | 1
| Detail description | NguyenVT | Done | 10 | 0 | 1 | 2 | 5 | 0 | 1
User Interface design
| - Learner | ThinhLP | Done | 10 | 2 | 2 | 4 | 2 | 0 | 0.5
| - Author | AnhDT | Done | 10 | 3 | 2 | 3 | 1 | 1 | 0.5
| - Manager | NguyenVT | Done | 10 | 0 | 0 | 0 | 2 | 8 | 0.5
| - Admin | AnhDT | Done | 10 | 2 | 2 | 2 | 3 | 0 | 0.5
| Algorithms | ThinhLP | Todo | 20
| Total |  |  | 147 | 32 | 31 | 30 | 26 | 17 | 11

## Sprint 11
Sprint 11
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Implement prototype | Course reviewing page | NguyenVT | Done | 15 | 4 | 2 | 3 | 2 | 2 | 1
| Teaching courses page | NguyenVT | Done | 10 | 2 | 2 | 2 | 2 | 2 | 1
Implement course pages | Implement course reviewing page | Hung PC | Done | 15 | 5 | 2 | 3 | 2 | 1 | 1
| Implement teaching course page | Hung PC | Done | 10 | 1 | 1 | 1 | 3 | 3 | 1
Document | Report 4
| Component diagram | ThinhLP | Done | 10 | 4 | 2 | 3 | 1 | 0 | 1
| Algorithms | ThinhLP | Done | 15 | 4 | 4 | 3 | 3 | 2 | 1
Report 5
| Introduction | AnhDT | Done | 5 | 5 | 0 | 0 | 0 | 0 | 1
| Database relationship diagram | ThinhLP | Done | 5 | 0 | 1 | 2 | 1 | 4 | 1
| Test plan | HungPC | Done | 25 | 2 | 5 | 4 | 3 | 4 | 1
| System testing test case | NguyenVT | Done | 25 | 2 | 4 | 3 | 4 | 4 | 1
Report 6
| Installation guide | AnhDT | Done | 15 | 3 | 4 | 3 | 2 | 3 | 1
| User guide | AnhDT | Done | 20 | 0 | 4 | 5 | 6 | 5 | 1
| Total |  |  | 135 | 32 | 31 | 32 | 29 | 30 | 10

## Sprint 12
Sprint 12
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Write paper | Abstract | ThinhLP | Done | 15 | 5 | 3 | 2 | 2 | 3 | 1
| Introduction | AnhDT | Done | 15 | 3 | 2 | 5 | 3 | 2 | 1
| Related works | HungPC | Done | 15 | 4 | 3 | 5 | 3 | 2 | 1
| Main Contribution | NguyenVT | Done | 15 | 5 | 2 | 4 | 2 | 3 | 1
Test | Admin features | AnhDT | Done | 20 | 4 | 3 | 3 | 4 | 5 | 1
| Manager features | HungPC | Done | 20 | 4 | 6 | 2 | 3 | 5 | 1
| Author features | NguyenVT | Done | 20 | 3 | 6 | 3 | 5 | 4 | 1
| Learner features | ThinhLP | Done | 20 | 2 | 4 | 6 | 5 | 4 | 1
| Total |  |  | 140 | 30 | 29 | 30 | 27 | 28 | 8

## Sprint 13
Sprint 13
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Write Paper | Result | ThinhLP | Done | 15 | 1 | 2 | 4 | 6 | 2 | 1
| Discussion | NguyenVT | Done | 15 | 3 | 3 | 3 | 3 | 3 | 1
| Conclusion and Feature Work | HungPC | Done | 15 | 5 | 2 | 3 | 2 | 2 | 1
| Acknowledgement + References | AnhDT | Done | 15 | 2 | 4 | 4 | 2 | 2 | 1
Fix Bugs | Reorder question | AnhDT | Done | 10 | 3 | 2.5 | 2.5 | 1 | 1 | 1
| Update skill information | HungPC | Done | 10 | 2 | 3 | 2 | 2 | 2 | 1
| Remove course | NguyenVT | Done | 10 | 2 | 2 | 2 | 2 | 2 | 1
| Add learner to plan | ThinhLP | Done | 10 | 2 | 2 | 1 | 2 | 6 | 1
| Total |  |  | 100 | 20 | 20.5 | 21.5 | 20 | 20 | 8